## Sheet1
Task | Start Date | End Date | Duration
Research topic selection | 2024-05-01 | 2024-06-01 | 1 month
Requirement gathering | 2024-06-01 | 2024-07-01 | 1 month
Study on research area | 2024-07-01 | 2024-08-01 | 1 month
Topic approval | 2024-08-01 | 2024-09-01 | 1 month
Project proposal draft submission | 2024-09-01 | 2024-10-01 | 1 month
Proposal presentation | 2024-10-01 | 2024-11-01 | 1 month
Research and select technology stack | 2024-10-15 | 2024-11-01 | 2 weeks
System planning and design | 2024-11-01 | 2024-12-01 | 1 month
Collect and prepare training data | 2024-12-01 | 2025-01-01 | 1 month
Model development and fine-tuning | 2025-01-01 | 2025-02-01 | 1 month
Model testing and validation | 2025-02-01 | 2025-03-01 | 1 month
Feature extraction | 2025-03-01 | 2025-04-01 | 1 month
Behavior analysis and scoring | 2025-04-01 | 2025-05-01 | 1 month
Progress presentation - 50% | 2025-05-01 | 2025-06-01 | 1 month
Prepare research paper | 2025-06-01 | 2025-07-01 | 1 month
Integration with other components | 2025-07-01 | 2025-08-01 | 1 month
Testing and validation | 2025-08-01 | 2025-09-01 | 1 month
Progress presentation - 90% | 2025-09-01 | 2025-10-01 | 1 month
Final thesis with proofreader sign-off | 2025-10-01 | 2025-11-01 | 1 month
Deployment and feedback | 2025-11-01 | 2025-12-01 | 1 month
Final presentation | 2025-12-01 | 2026-01-01 | 1 month